## 工作表1
Team | Group7 Go
Team Location | Seattle
ID | US: As a | US: I want to | US: So that | Acceptance Criteria | Priority | Story Points | Sprint Assigned | Status
2 | Paient | I want to the AI-powered healthcare diagnostics app to provide reliable and accurate disease detection | Health data is being analyzed comprehensively and receive early and effective treatment based on trustworthy results. | 1. The AI’s diagnosis accuracy should be above 95%, with confidence scores visible for transparency. 2. Receive an explanation of their diagnostic results in simple | Medium | 3 | 0 | In progress
4 | Patient | The app to allow me to track medication adherence and reminders. | I can ensure I am following my treatment plan. | 1. Users can set medication schedules and receive reminders. 2. Users can share adherence data with their healthcare providers. | Medium | 3 | 0 | In progress
5 | Nurse | I want to use an AI-powered diagnostic tool to quickly access patient data and risk assessments | I can make informed decisions about patient care in real-time. | 1. The AI diagnostic tool must retrieve and display patient data and risk assessments within 5 seconds of input to ensure real-time decision-making. | Medium | 1 | 0 | In progress
6 | Nurse | I want to access AI-generated diagnostic recommendations from patient data | I can assist doctors in providing timely and accurate treatment | 1. The AI tool must provide diagnostic recommendations with a confidence score (e.g., 85%) and a summary of the underlying data used for the recommendation to allow nurses and doctors to make informed decisions. | Medium | 1 | 0 | In progress
11 | IT Administrator | Need the app to be compatible with our existing hospital information system | I can integrate it seamlessly into our current workflow. | 1. The system must be able to pull and push data in real-time from the existing hosptial information system without errors or data loss. 2. Data retrieval within 2-3 seconds | Low | 3 | 0 | In progress
3 | Patient | The app to help me track my treatment progress and compare my current condition with past diagnostics | I can monitor my recovery and stay motivated | 1. The app should display a visual dashboard that includes historical data (e.g., graphs or trend lines) of key metrics (e.g., blood pressure, cholesterol levels). | Low | 3 | 0 | Done
7 | Doctors | I want a database schema that stores appointment details (such as date, time, type of appointment, and diagnosis type) | so that the system can efficiently manage and retrieve appointment information for each patient | 1. The database schema should include fields for: Appointment Date, Appointment Time etc 2. The schema should support efficient querying and filtering of appointments by patient ID, date, and type. 3. It should include relationships between patient information and appointment details (e.g., foreign keys linking to patient records). 4. The schema should support future extensions for storing additional appointment attributes (e.g., doctor’s notes, appointment status). | Low | 5 |  | Done
12 | Doctors | The AI-powered diagnostic app to integrate medical imaging (X-rays, CT scans, MRI) with AI-based analysis | I can detect diseases more accurately and efficiently | 1. Medical imaging formats are supported 2. AI-based analysis is integrated 3. Accuracy threshold met | Low | 5 | 1 | Done
1 | Patient | The app to send me reminders for upcoming appointments related to my diagnosis | I can stay on top of my healthcare without missing important visits. | 1. Notification preferences can include push notifications, emails, or SMS. | Low | 3 | 0 | Done
8 | Hospital administrator | The app to follow strict privacy protocols (HIPAA compliance, secure data handling) | Ensure patient data is protected | 1. HIPAA compliance ensured 2. Data access restrictions applied 3. Response to security incidents | Low | 1 | 0 | Done
9 | Patient | The app to allow me to securely access my diagnostic reports while ensuring my personal health information is protected | I can stay informed about my health without compromising my privacy | 1. Enable 2FA (Two-Factor Authentication) 2. The patient can view a list of their available diagnostic reports categorized by date and type. | Low | 3 | 0 | Done
10 | IT Administrator | Ensure the AI diagnostic system is secure, reliable, and compliant with healthcare data regulations | Patient information is protected and the system operates smoothly | 1. The system must undergo regular penetration testing and vulnerability assessments 2. Multi-factor authentication (MFA) is required for users accessing the system from outside the hospital network. | Low | 3 | 0 | Done
Date | Sprints | Scrum Master | Project Owner | Developer1 | Developer 2 | Developer 3 | Developer 4
2024-10-02 | 1 | Kehan Tang | Zhaoju Liu | Yuyan Li | Lin Yang | Niharika |  | 1. What work did we complete yesterday? Get to know the project, identified core user needs 2. What do we plan to work on today? Finalize the project backlog and prioritize the user stories we created. refining requirements for integrating medical imaging and genetic data into the app. working on user stories that address ethical concerns and privacy issues, which are critical for healthcare applications. 3. Any blocking? Data Access: Difficulty in obtaining comprehensive, high-quality datasets (medical images, genetic information) for training and testing the AI system.
2024-10-09 | 2 | Yuyan Li | Niharika | Kehan Tang | Zhaoju Liu | Lin Yang |  | 1. What work did we complete yesterday? Finalize the project backlog and prioritize the user stories we created. refined requirements for integrating medical imaging and genetic data into the app. worked on user stories that address ethical concerns and privacy issues, which are critical for healthcare applications. 2. What do we plan to work on today? We synced up the progress of some high priority core functions like disease detection, we basically finished them and marked them as done, and we moved on to new tasks. We clarified the different roles in users and added more user stories. Adjusted the priorities of some tasks based on the actual needs. 3. Any blocking? Understanding the complexity and scalability of system since it’s associated with a lot of stakeholders.
2024-10-17 | 3 | Lin Yang | Yuyan Li | Kehan Tang | Zhaoju Liu | Niharika | Zhilin Li | 1. What work did we complete yesterday? We synced up the progress of some high priority core functions, we basically finished them and marked them as done, and we moved on to new tasks. We clarified the different roles in users and added more user stories. Adjusted the priorities of some tasks based on the actual needs. 2. What do we plan to work on today? We will sync with the frontend developers to ensure that the notification, treatment plan and diagnostic report features are displayed clearly and friendly for patients. Working with developers from hospital IT department to pull the data we required from their information system such as doctors' schedule and API integrations between two systems. 3. Any blocking? Currently, we’re facing some performance bottlenecks with database queries, especially when handling large amounts of patient data. We will discuss this with the database developer to see if we can optimize the query structure or use caching to improve performance.
2024-10-24 | 4 | Niharika | Kehan Tang | Zhilin Li | Yuyan Li | Zhaoju Liu | Lin Yang | 1. What work did we complete yesterday? We have reviewd and completed 7 User stories. Updated the priority ranking. 2. What do we plan to work on today? Focusing on the 5 remaining 'In Progress' User stories, also teams to breakdown on specific tasks and pre-planning session on the completion of the User stories. 3. Any blocking? No current blockers identified and team has clear path forward with remaining stories.
5